| CHUKA |  | UNIVERSITY |
| --- | --- | --- |

UNIVERSITY EXAMINATIONS

EXAMINATION FOR THE AWARD OF DEGREE OF BACHELOR OF PROJECT AND PLANNING MANAGEMENT

PPMA 111: PROJECT IDENTIFICATION

STREAMS: PPMA (ODEL) 				    		     TIME: 2 HOURS

DAY/DATE: TUESDAY 09/04/2024			           	         11.30 A.M. – 1.30 P.M.

INSTRUCTIONS:

- Answer question one and two more

# QUESTION ONE (30 MARKS)

- Define the following terms as used in project identification.

- Project identification						(2 marks)

- Problem analysis 							(2 marks)

- Project 								(2 marks)

- Outline five objectives of community needs assessment. 			(5 marks)

- Strategy analysis is a very key phase of the logframe approach. Outline any four key possible criteria for strategy selection. 					(4 marks)

- Outline five pitfalls that should be avoided while carrying out stakeholder analysis.											(5 marks)

- Explain various problems faced by the community members while initiating projects.											(10 marks)

# QUESTION TWO (20 MARKS)

- Using clear diagrams explain the following stakeholder analysis tools and techniques.

- Stakeholder positioning 							(4 marks)

- Stakeholder profiles 							(4 marks)

- Mendelow matrix 								(4 marks)

- Explain two types of project identification approaches clearly bringing out two advantages in each case. 									(8 marks)

# QUESTION THREE (20 MARKS)

- Describe various techniques of generating project ideas. 			(10 marks)

- Using relevant examples in each case describe various components of the logical framework matrix. 								(10 marks)

# QUESTION FOUR (20 MARKS)

- Outline any four characteristics of a good needs assessment. 		(4 marks)

- Describe any three tools and techniques used to identify community needs.	(6 marks)

- Describe five principles of participatory rural appraisal. 			(10 marks)

# QUESTION FIVE (20 MARKS)

- Write short notes on the following participatory rural appraisal tools and techniques.

- Venn diagram 								(3 marks)

- Pairwise ranking 								(3 marks)

- Community mapping 							(3 marks)

- Historical mapping 							(3 marks)

- Using relevant examples explain various characteristics of good governance. (8 marks)

…………………………………………………………………………………………………….