| CHUKA |  | UNIVERSITY |
| --- | --- | --- |

UNIVERSITY EXAMINATIONS

FIRST YEAR EXAMINATION FOR THE AWARD OF DEGREE OF MASTER OF PUBLIC HEALTH

PUHE 812: PROJECT MANAGEMENT AND EVALUATION

STREAMS: Y1S2								TIME: 3 HOURS

DAY/DATE: MONDAY 08/04/2024				        8.30 A.M. – 11.30 A.M.

INSTRUCTIONS:

- Do not write anything on the question paper.

- Mobile phones and any other reference materials are NOT allowed in the examination room.

- Answer ALL questions.

- Number ALL your answers and indicate the order of appearance in the space provided in the cover page of the examination answer booklet.

- Write  your answers legibly and use your time wisely

ANSWER ALL QUESTIONS (100 MARKS)

1. Some projects fail while others succeed.

a) Explain five measures of a successful project.				(5 marks)

b) Explain five reasons why projects fail.					(5 marks)

c) A project has the following activity details:

| Activity | Immediate predecessors | Activity time (weeks) |
| --- | --- | --- |
| A | - | 3 |
| B | - | 4 |
| C | - | 3 |
| D | C | 12 |
| E | B | 5 |
| F | A | 7 |
| G | E,F | 3 |

Draw a Gnatt chart to represent the project and indicate the duration. 		(10 marks)

2. Projects have a life cycle. Discuss the stages and four activities in each stage.	(20 marks)

3.As the new Project Manager for the Choo Bora ni Heshima Project, you are required to include stakeholders in your project.

a) Discuss the process you will use to manage the stakeholders.		(10 marks)

b) Explain five ways stakeholders can break your project.			(10 marks)

4.Project appraisal is an effective tool in project management. Discuss five methods of project appraisal.										(20 marks)

5. Before embarking on any project, you will conduct an environmental analysis.

a) Explain five reasons why it is important to analyse the project environment before initiating a project.								(10 marks)

b) Discuss how you will use SWOT to analyse the environment for your Choo Bora ni Heshima Project.								(10 marks)

---------------------------------------------------------------------------------------------------------------------